## Sheet1
S.N | Work elements | Quarter wise | [7 empty] | Duration in months
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | Literature survey | [8 empty] | 3
2 | Procurement of raw meterials and chemicals and machineries | [8 empty] | 6
3 | Development of deccani wool based nonwoven for mulching material | [8 empty] | 9
4 | Designing of Natural fibre based nonwoven mulching material for field trials.Improvement of durability with biopolymer. | [8 empty] | 9
5 | Synthesis of microencapsulated micronutrient and prebiotic. | [8 empty] | 9
6 | Application of micronutrient to developed mulching material for improvement of crop production and soil Enrichment. | [8 empty] | 9
7 | Testing of the developed products for strength, biodegradability, solar degradation. | [8 empty] | 12
8 | Field trial of the developed natural fibre based mulching material for the phenology and agronomic traits of the selected crops. | [8 empty] | 12
9 | Comparative study of Natural fibre based mulching material with and without added nutrient with conventional polyethylene mulch. | [8 empty] | 12
10 | Data Analysis of Field trials. | [8 empty] | 12
11 | Submission of report. | [8 empty] | 6